## Slide 1
PROJECT MANAGEMENT FOR SOFTWARE DEVELOPMENT
Agile
Ship small slices of working software frequently, show them to real users, and let what you learn reorder what you build next.
PLAN
BUILD
SHIP
LEARN
every 1–2 weeks, the loop closes and the plan changes
20
slides
Notes: Agile is a set of values about decision-making under uncertainty, not a process. The frameworks are implementations of those values.

## Slide 2
01 / FOUNDATIONS
Agile is not a process. It is a way of betting.
The concrete methods — Scrum, Kanban, XP — are implementations. The values underneath them are about how you make decisions when you cannot know the answer up front.
The core premise
You cannot fully specify software before building it. Requirements change, users discover what they want by using things, and estimates degrade the further out you look.
The consequence
So instead of one long bet, you make many short bets and correct course after each one. Everything else in Agile follows from that single move.
COST OF BEING WRONG
Discover in 2 weeks
cheap
Discover in 3 months
painful
Discover after launch
expensive
Agile shortens the distance between a decision and the evidence that it was wrong.

## Slide 3
01 / FOUNDATIONS
The Agile Manifesto — four values, 2001
Seventeen practitioners, one ski lodge, four sentences. Each has the same shape: we value the left more than the right.
Individuals and interactions
over
Processes and tools
Working software
over
Comprehensive documentation
Customer collaboration
over
Contract negotiation
Responding to change
over
Following a plan
The right column still has value. The left column has MORE value — that nuance gets lost constantly.

## Slide 4
02 / THE STRUCTURAL DIFFERENCE
One long bet versus many short bets
WATERFALL
Requirements
Design
Build
Test
Release
feedback arrives after months — correction is expensive
AGILE
Iteration 1
plan · build · test · ship
Iteration 2
plan · build · test · ship
Iteration 3
plan · build · test · ship
Iteration N
plan · build · test · ship
feedback arrives every 1–2 weeks — correction is cheap
The key difference is feedback latency. Waterfall discovers it was wrong at the end. Agile discovers it was wrong every two weeks, when correction is cheap.

## Slide 5
03 / SCRUM
Three roles, three different questions
Scrum is a time-boxed framework. Work happens in fixed-length Sprints, and exactly three roles own exactly three concerns.
Product Owner
the WHAT and WHY
Owns and orders the backlog. Single wringable neck for value delivered. Needs real authority — a PO without decision power is the most common way Scrum quietly fails.
Scrum Master
the PROCESS
Removes blockers and protects the sprint from mid-flight scope injection. Not a manager, not a secretary, not a status collector.
Development Team
the HOW
Self-organizing and cross-functional, ideally 3–9 people. Decides how the work gets built and commits to what fits in the sprint.
No project manager role. That is deliberate — planning authority sits with the team, value authority with the PO.

## Slide 6
03 / SCRUM
Three artifacts and one contract
Product Backlog
Everything that might get built, ordered by value. Living — always re-prioritized, never frozen.
Sprint Backlog
The slice the team committed to this sprint. Frozen once the sprint starts.
Increment
The shippable output at sprint end. Must meet the Definition of Done.
Definition of Done
The shared, explicit, non-negotiable bar every increment must clear. Without it, "done" means "merged" and QA finds the truth three sprints later.
Code reviewed
Tests written & green
Merged to main
Deployable
AC verified
Docs updated

## Slide 7
03 / SCRUM
The sprint loop
Refine
Plan
Build
Review
Retro
SPRINT
1–2 weeks
1
Refine
Backlog refinement runs continuously mid-sprint: size items, write acceptance criteria, split anything too big.
2
Plan
Sprint Planning picks the slice and breaks it into tasks. Output: a sprint goal and a frozen sprint backlog.
3
Build
The team builds. A 15-minute daily standup syncs and surfaces blockers — it is not a status report to a manager.
4
Review
Demo working software to stakeholders. Real feedback enters here and reorders the product backlog.
5
Retro
Improve how the team works, not what it built. Action items need owners or the retro is theatre.
The loop is the product. Everything else in Scrum exists to keep it turning on time.

## Slide 8
03 / SCRUM
Four ceremonies, four timeboxes
Every ceremony has a purpose and a hard limit. When a ceremony overruns, it has usually drifted into doing another one's job.
Sprint Planning
Start of sprint
2–4 hrs
Decide what is in, break it into tasks, agree a sprint goal.
Daily Standup
Every day
15 min
Sync and surface blockers. Not a status report to a manager.
Sprint Review
End of sprint
1–2 hrs
Demo working software, gather feedback from real stakeholders.
Retrospective
End of sprint
1 hr
Improve how the team works — process, not product.

## Slide 9
04 / THE WORK
Big things decompose into shippable things
Each level exists so the level below it can be estimated. If a story cannot be sized, it is still an epic.
Initiative / Theme
quarters
Strategic outcome. Never built directly — it exists to give epics a reason.
Epic
weeks to months
A body of work too big to finish inside one sprint.
User Story
days
A slice of user-visible value, sized and testable.
Task
hours
How a story gets built. Written and owned by devs.
Bugs enter at story level — they are work with acceptance criteria like anything else.

## Slide 10
04 / THE WORK
Anatomy of a user story
TEMPLATE
As a <type of user>
I want
<some capability>
So that
<some benefit>
Acceptance Criteria
The testable conditions that define "done" for this story. Without AC, a story is a wish — and "done" becomes a matter of opinion at review time.
INVEST — the story quality checklist
I
Independent
Ships without waiting on another story.
N
Negotiable
Describes intent, not implementation.
V
Valuable
A user or the business gains something.
E
Estimable
The team can size it.
S
Small
Fits comfortably inside one sprint.
T
Testable
You can prove it works.

## Slide 11
04 / THE WORK
How a story actually moves
Backlog
Refined
Committed
In Progress
In Review
Testing
Done
changes requested
bug found in testing
Blocked
The one state that matters operationally. A story sitting in Blocked is the single most useful signal a standup produces — everything else in that meeting is optional.
What the board is telling you
Everything piled in Testing — the team is integrating late. Everything piled in In Review — reviews are not anyone's priority. Nothing ever Blocked — people are working around problems silently.

## Slide 12
05 / KANBAN
Kanban: flow instead of iterations
No sprints, no fixed commitments. Work is pulled continuously and the control mechanism is the WIP limit — a hard cap on how many items may sit in a column.
Backlog
∞
STORY-10
STORY-11
STORY-12
Ready
WIP 3
STORY-20
STORY-21
In Progress
WIP 2
STORY-30
STORY-31
FULL — pull nothing new
Review
WIP 2
STORY-40
Done
∞
STORY-50
STORY-51
If "In Progress" is full, you cannot start new work — you must go help finish existing work. That is the entire mechanism, and it optimizes for throughput rather than individual utilization.

## Slide 13
05 / KANBAN
The most counterintuitive true thing in Agile
Cycle Time = Work In Progress ÷ Throughput
Little's Law
Halve your WIP, halve your cycle time.
Throughput is roughly fixed by team capacity, so the only lever you actually control is how much work is open at once. Teams instinctively start more things when they feel behind, which is exactly backwards: it lengthens every item's cycle time without adding capacity.
WIP 8
cycle time 8 days
throughput unchanged: 1 item/day
WIP 4
cycle time 4 days
throughput unchanged: 1 item/day

## Slide 14
05 / KANBAN
Scrum or Kanban — pick by inflow, not by fashion
SCRUM
KANBAN
Cadence
Fixed sprints
Continuous flow
Commitment
A sprint goal
None — pull as capacity frees
Change mid-cycle
Discouraged
Fine, just re-prioritize
Key metric
Velocity
Cycle time / throughput
Roles
Three, prescribed
None prescribed
Best for
Feature work needing planning
Support, ops, unpredictable inflow
Many teams run Scrumban: sprints for planning cadence, WIP limits for flow control. That is a legitimate answer, not a cop-out.

## Slide 15
06 / ESTIMATION
Story points measure size, not hours
Points bundle complexity, uncertainty and effort into one relative number. Humans are bad at absolute duration estimates and good at comparative ones.
1
2
3
5
8
13
21
↑ gaps widen because certainty falls — a 13 is not "13 ones", it is "we are guessing"
Planning Poker
Everyone estimates simultaneously and privately, then reveals at once. Simultaneity prevents anchoring on the loudest voice in the room.
Divergence means people understand the story differently. That conversation is the actual value — the number is a by-product.
Velocity is not a performance metric
It is a forecasting tool the team uses on itself. The moment velocity becomes a target, teams inflate estimates and the number stops meaning anything. This is Goodhart's Law and it happens with near-total reliability.
Never compare velocity across teams. Points are a private unit — one team's 5 has no relationship to another's.

## Slide 16
06 / ESTIMATION
Velocity: what a healthy team looks like
Chart: Points completed per sprint
| S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
Points completed | 22 | 31 | 27 | 35 | 33 | 38 | 36 | 37
Read it as a range
Forecast with the last 3–5 sprints as a band (here: 33–38), not with a single average. The variance is information, not noise.
Ramp is normal
New teams take 3–4 sprints to stabilise. Judging a team on sprint 1 velocity tells you nothing except that they are new.
A perfectly flat velocity line is usually a sign of estimate-padding, not of stability.

## Slide 17
06 / ESTIMATION
Burndown: the shape matters more than the endpoint
Chart: Points remaining across a 10-day sprint
| D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Ideal | 36 | 32 | 28 | 25 | 21 | 18 | 14 | 10 | 5 | 0
Healthy actual | 36 | 34 | 30 | 29 | 24 | 22 | 16 | 11 | 5 | 0
Late-integration | 36 | 36 | 35 | 35 | 34 | 33 | 31 | 26 | 14 | 0
Healthy
Work comes off steadily, roughly tracking the ideal line, with small plateaus where reviews and testing happen.
The cliff
Flat early, vertical at the end. The team worked in parallel and integrated late. It is a smell, not a success — nothing was truly done until the last day.

## Slide 18
07 / ENGINEERING PRACTICES
Without these, Agile becomes short waterfalls with more meetings
Most of these come from Extreme Programming. They are what make a two-week feedback loop physically possible.
Continuous Integration
Merge to main frequently. Automated build and test on every push, and a red pipeline stops the line.
Automated testing
You cannot iterate quickly on code you are afraid to change. Tests buy the courage to refactor.
Continuous refactoring
Small, safe, constant — not a "refactoring sprint" scheduled for never.
Short-lived branches
Long branches recreate the integration problem Agile was invented to solve.
Feature flags
Decouple deploy from release so unfinished work can ship dark and be turned on later.
Definition of Done
Explicit, shared, includes tests plus review plus deployable. Otherwise "done" is an opinion.
Ceremonies without engineering practices is the single most common way an "Agile transformation" fails.

## Slide 19
08 / WHAT GOES WRONG
Eight ways Agile turns into theatre
Water-Scrum-Fall
Big upfront requirements, sprints in the middle, one release at the end.
Zombie standups
Round-robin status reports delivered to the Scrum Master.
Velocity as a KPI
Management tracks points per person. Estimates inflate immediately.
No Definition of Done
"Done" means merged; QA finds the truth three sprints later.
Retro theatre
Same issues raised every sprint, no owners, nothing changes.
Backlog as a landfill
800 items, nothing pruned, priority order meaningless.
Scope injection
The PO adds work mid-sprint and nobody stops them.
Absentee Product Owner
Devs guess at requirements. The role was given to someone with no time.
The common root cause
Almost every item above is the same failure wearing a different hat: the organisation kept its old decision-making structure and asked only the development team to change. Agile is a change to who decides what, and when — if that does not move, nothing does.

## Slide 20
09 / LIMITS
When Agile is the wrong choice
Agile assumes requirements are uncertain and iteration is cheap. Where neither holds, it fits badly — and saying so is not heresy.
Safety-critical & regulated
Avionics, medical devices, anything where upfront verification is a legal requirement rather than a preference.
Fixed-scope fixed-price contracts
The contract structure fights the methodology. You cannot welcome changing requirements when scope is the payment term.
Genuinely well-understood work
A straightforward migration with a known destination does not need iterative discovery. It needs a plan and execution.
Solo or two-person projects
Most of the ceremony is coordination overhead for coordination you do not have.
Scaling frameworks (SAFe, LeSS, Nexus) solve coordination. If the real problem is ownership or architecture, no framework fixes it.

## Slide 21
IN ONE SENTENCE
Ship small slices of working software frequently, show them to real users, and let what you learn reorder what you build next.
What most teams get wrong
They adopt the ceremonies and skip the engineering practices, then wonder why iterating still hurts.
What to do on Monday
Pick one loop and shorten it. Cut WIP, or write acceptance criteria before work starts, or make the retro produce one owned action. One change, measured.